## Tabelle1
| 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03
Every day start with a stand up and bring up the previous day and discuss transpired and included incomplete tasks. Stand up at the end to sum what we have done. | Day 1 | Day 2 | Day 3 | Day 4 (Sprint 1 end) | Day 5 | Day 6 | Day 7 (Sprint 2 end) | Day 8 | Day 9 | Day 10
| Create Task | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | D-DAY
| Approve Task | Search in dummy DB | - Redo Post&Get | Search optimization | Plan design |  |  | Unit Test
| Planning | Find API | - Search into DB | Find API for text analyze
| - Flowchart | Find Database | - Post result | songId, cut correctly
| - Excel plan | Integrate DB | Cut lyrics
| - TODO | - RestController
| Create First Step | - Redo Post&Get
| Find API | - Search into DB
| Find Database | - Post result
| Start GitHub | Find API for text analyze
Name for Project
Create a dummy DB
Search in dummy DB