## Tabelle1
| 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03
Every day start with a stand up and bring up the previous day and discuss transpired and included incomplete tasks. Stand up at the end to sum what we have done. | Day 1 | Day 2 | Day 3 | Day 4 (Sprint 1 end) | Day 5 | Day 6 | Day 7 (Sprint 2 end) | Day 8 | Day 9 | Day 10
| Create Task | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | StandUp x2 | D-DAY
| Approve Task | Search in dummy DB | - Redo Post&Get | Search optimization | Plan design | Create Unit Test for class | Presentation | Picture rep result
| Planning | Find API | - Search into DB | Find API for text analyze | Search optimization | Search optimization | Create Unit Test for class
| - Flowchart | Find Database | - Post result | songId, cut correctly | Plan slides | Plan slides | Loading icon
| - Excel plan | Integrate DB | Cut lyrics |  | Unit Test | Choose a colour scheme | Make ppt
| - TODO | - RestController |  |  |  | Design | Design
| Create First Step | - Redo Post&Get |  |  |  | Update old code | Picture rep
| Find API | - Search into DB |  |  |  | Loading icon | Logo?
| Find Database | - Post result |  |  |  |  | Big merge
| Start GitHub | Find API for text analyze
Name for Project
Create a dummy DB
Search in dummy DB

## RetroSprint
| Sprint 1 | Sprint 2 | Sprint 3
+ | Small success stories every day
- | Work more parrallel
+ | Good teamwork
- | Work more parrallel
+ | New skills
- | Work more parrallel
+ | Every voice is heard
+ | Good dynamic
+ | Good flow
+ | Good balance of difficulty
- | Not everyone has had a chance to code

## Design
Design |  |  | Färgval
Contrast |  | bakgrund | #D5EED5
Readability |  | text | svart
Colour (calm) |  | kontrast | vit
|  | menybar | C5DBC5
|  | font | Helvetica
Adapt to result
5*3 result options
Inspo
Dall-E
Google
Resurs för menybar | https://codepen.io/Calloumi/pen/DyKMbj
Större markör